# Recycling Public Advisory Council

# Meeting Agenda

Thursday, October 25, 2012

10:00 a.m. – 12:00 p.m.

DNREC Lukens Drive Office

391 Lukens Drive

New Castle 19720

- Call to Order, Introductions

- Public Comments (20 minute cap, priority given to written comments)

- Approval of Minutes from September 27, 2012 Meeting

- Bottle Fee Collection Update

- SJR 8 - Carpet Recycling Strategy Subcommittee Meeting Report Out

- SR 24 - Plastic Bags, Meeting Report Out

- Annual RPAC Report

- Commercial Recycling Report

- Recycling Market Update

- Old/New Business

- Additional Public Comments

- Plastics To Oil Demonstration

- Next Meeting: November 29, 2012, DelDot Felton/Farmington Room, 800 Bay Road, Dover 19903

- Adjourn

| Item | Event | SB 234 Due Date | SB 234 Line # (Engrossed) | Notes/Status/Work Projection |
| --- | --- | --- | --- | --- |
| 1 | Administration, DNREC and RPAC collaborate to expand membership | ASAP | 230 | Complete |
| 2 | RPAC Annual Reports commence | 11/1/2010 | 263 | First report completed. Future reports pending. |
| 3 | RPAC Reporting Guidance due | 12/1/2010 | 203 | In May 2011 the finalized Reporting Guidance for the required reporting of CY2011 data was distributed along with DSM’s CY2010 voluntary reporting survey request. In this manner the CY2010 survey will serve as a trial run for the required reporting commencing in 2012. |
| 4 | Bottle Fee Begins | 12/1/2010 | 355 | Implemented. Fees collected are about 60% of expected. |
| 5 | Controller General Approval for recycling fund expenditures | 12/1/2010 | 155 | Funding is approved. |
| 6 | Consumer Deposit recovery ability ends | 2/1/2011 | 386 | Complete |
| 7 | Retailer Deposit recovery ability ends | 3/1/2011 | 390 | Complete |
| 8 | Grant & Loan Program Starts | 2011 | 148 | Initial cycle complete. Grant activities underway for second cycle (focus on multi-family residential programs). Third cycle to start in early 2013. |
| 9 | DSWA ceases curbside collection and Hauler/ Municipal Single Family Curbside starts | 9/15/2011 | 71 | DSWA ended curbside collection of recyclables on 3/31/11. Single-family residential deadline has passed. Only minor issues noted and quickly resolved. DNREC continues to provide outreach to encourage recycling. |
| 10 | Annual Recyclables Reports commence | 2/15/2012 | 204 | Report requests were sent out by DSM 2/1/12. |
| 11 | RPAC Commercial Report due | 11/1/2012 | 106 | Commercial subcommittee meetings underway. Report drafted and under review. |
| 12 | Multifamily recycling starts | 1/1/2013 | 89 | DNREC held several workshops for public/property managers in 2012. Outreach will continue. |
| 13 | Commercial Recycling starts | 1/1/2014 | 109 | Development of outreach will be begin 1/1/2013. |
| 14 | RPAC Goals Assessment Report due | 11/1/2014 | 212 | Preparation will begin 7/1/2014. |
| 15 | Bottle Fee ends | 12/1/2014 | 379 | An assessment of any remaining funds will be made and a plan for final expenditures will be made if necessary. |
| 16 | Grant and Loan Program Ends | 2014 | 149 | Comprehensive report will be available via RPAC Annual Report. |
| 17 | Diversion Goals tier 1 | 1/1/2015 | 195 | Status report and recommendations will be available via RPAC Annual Report. |
| 18 | Diversion Goals tier 2 | 1/1/2020 | 195 | Status report and recommendations will be available via RPAC Annual Report. |